## All
Phase | Integration | Description | Requirements | Timeline | Queries
1 | Party order | At the end of this phase an user can able to place party order foods according the ui/ux flow designed | Phase 1 Requirement | Phase 1 Timeline | Phase 1 Queries
2 | Subscription
3 | Instant order
Shero US Website
Phase | Integration | Description | Requirements | Timeline | Queries | Reference Links
1 | Shero US Website - Phase 1 | Single meal order | Shero US Phase 1 Requirement | Shero US Phase 1 Timeline | Shero US Phase 1 Queries | https://shef.com/
2 | Shero US Website - Phase 2 | Subscriptions | Shero US Phase 2 Requirement | Shero US Phase 2 Timeline | Shero US Phase 2 Queries | https://www.cookunity.com/
3 | Shero US Website - Phase 3 | Party orders | Shero US Phase 3 Requirement | Shero US Phase 3 Timeline | Shero US Phase 3 Queries
4 | Shero US Website - Phase 4 | Sweets & snacks | Shero US Phase 4 Requirement | Shero US Phase 4 Timeline | Shero US Phase 4 Queries

## Shero US Phase 1 - Requirement
| Required | Description | Staus | Asset link
1 | Full functional & logic document | We need it the understanding of what we require and keep us in check that we are in right track | Got it | https://drive.google.com/file/d/1DBc21MNGnGW87nji_bPVv4QNZTM_OY3i/view?usp=sharing
2 | VPS server setup & access | This will be used to deploy of our web app | Yet to get
3 | Payment gateway details | To integrate the payment to orders.. We should register it with an thirdparty payment gateway provider if we dont have one | Yet to get
4 | Sms gateway | This will be used to SMS communications like OTP, order placement etc.. Same like payment gateway we need to register sms in third party providers | Yet to get
5 | SMTP buisness mail ID | This will act as our from mail ID for the communication to users | Yet to get
6 | All related API's | API's that are necessary for the party orders flow like products, POS connection API etc | Yet to get

## Shero US Phase 2 - Requirement
| Required | Description | Staus | Asset link
1 | Full functional & logic document | We need it the understanding of what we require and keep us in check that we are in right track | Got it | https://drive.google.com/file/d/1DBc21MNGnGW87nji_bPVv4QNZTM_OY3i/view?usp=sharing
2 | VPS server setup & access | This will be used to deploy of our web app | Yet to get
3 | Payment gateway details | To integrate the payment to orders.. We should register it with an thirdparty payment gateway provider if we dont have one | Yet to get
4 | Sms gateway | This will be used to SMS communications like OTP, order placement etc.. Same like payment gateway we need to register sms in third party providers | Yet to get
5 | SMTP buisness mail ID | This will act as our from mail ID for the communication to users | Yet to get
6 | All related API's | API's that are necessary for the party orders flow like products, POS connection API etc | Yet to get

## Shero US Phase 3 - Requirement
| Required | Description | Staus | Asset link
1 | Full functional & logic document | We need it the understanding of what we require and keep us in check that we are in right track | Got it | https://drive.google.com/file/d/1DBc21MNGnGW87nji_bPVv4QNZTM_OY3i/view?usp=sharing
2 | VPS server setup & access | This will be used to deploy of our web app | Yet to get
3 | Payment gateway details | To integrate the payment to orders.. We should register it with an thirdparty payment gateway provider if we dont have one | Yet to get
4 | Sms gateway | This will be used to SMS communications like OTP, order placement etc.. Same like payment gateway we need to register sms in third party providers | Yet to get
5 | SMTP buisness mail ID | This will act as our from mail ID for the communication to users | Yet to get
6 | All related API's | API's that are necessary for the party orders flow like products, POS connection API etc | Yet to get

## Shero US Phase 4 - Requirement
| Required | Description | Staus | Asset link
1 | Full functional & logic document | We need it the understanding of what we require and keep us in check that we are in right track | Got it | https://drive.google.com/file/d/1DBc21MNGnGW87nji_bPVv4QNZTM_OY3i/view?usp=sharing
2 | VPS server setup & access | This will be used to deploy of our web app | Yet to get
3 | Payment gateway details | To integrate the payment to orders.. We should register it with an thirdparty payment gateway provider if we dont have one | Yet to get
4 | Sms gateway | This will be used to SMS communications like OTP, order placement etc.. Same like payment gateway we need to register sms in third party providers | Yet to get
5 | SMTP buisness mail ID | This will act as our from mail ID for the communication to users | Yet to get
6 | All related API's | API's that are necessary for the party orders flow like products, POS connection API etc | Yet to get

## Shero US Phase 1 - Timeline
Shero App Plan Phase 1- Timeline
S.no | Page/Section/Function | Timeline | Status | Estimated Hours | Hours Taken
1 | Project setup (Next.js + Prisma + Postgres) | Day 1 | Yet to be started | 2 hrs
2 | DB schema design | Day 2–3 | Yet to be started | 3 hrs
3 | UI/UX – Lovable screens integration | Day 3–6 | Yet to be started | 8 hrs
4 | Auth system (Login/Signup + session) | Day 5–6 | Yet to be started | 3 hrs
5 | Homepage + ZIP validation | Day 6–7 | Yet to be started | 2 hrs
6 | Delivery radius logic | Day 7 | Yet to be started | 1.5 hrs
7 | Menu API + UI binding | Day 8–9 | Yet to be started | 3 hrs
8 | Cart system | Day 9–10 | Yet to be started | 2 hrs
9 | Checkout flow | Day 10–11 | Yet to be started | 3 hrs
10 | Stripe payment integration | Day 11–12 | Yet to be started | 3 hrs
11 | Order placement + DB | Day 12 | Yet to be started | 2 hrs
12 | Notifications (Email) | Day 13 | Yet to be started | 1 hr
13 | User dashboard | Day 13–14 | Yet to be started | 2 hrs
14 | Admin – Menu management | Day 14–15 | Yet to be started | 2 hrs
15 | Admin – Order management | Day 15–16 | Yet to be started | 2 hrs
16 | Admin – ZIP control | Day 16 | Yet to be started | 1 hr
17 | Compliance pages | Day 16 | Yet to be started | 0.5 hr
18 | Security & validation | Day 17 | Yet to be started | 1.5 hrs
19 | Testing + bug fixing | Day 17–18 | Yet to be started | 2 hrs
20 | Deployment | Day 18 | Yet to be started | 1 hr

## Shero US Phase 2 - Timeline
Shero App Plan Phase 1- Timeline
S.no | Page/Section/Function | Timeline | Status | Estimated Hours | Hours Taken
1 | Project setup (Next.js + Prisma + Postgres) | Day 1 | Yet to be started | 2 hrs
2 | DB schema design | Day 2–3 | Yet to be started | 3 hrs
3 | UI/UX – Lovable screens integration | Day 3–6 | Yet to be started | 8 hrs
4 | Auth system (Login/Signup + session) | Day 5–6 | Yet to be started | 3 hrs
5 | Homepage + ZIP validation | Day 6–7 | Yet to be started | 2 hrs
6 | Delivery radius logic | Day 7 | Yet to be started | 1.5 hrs
7 | Menu API + UI binding | Day 8–9 | Yet to be started | 3 hrs
8 | Cart system | Day 9–10 | Yet to be started | 2 hrs
9 | Checkout flow | Day 10–11 | Yet to be started | 3 hrs
10 | Stripe payment integration | Day 11–12 | Yet to be started | 3 hrs
11 | Order placement + DB | Day 12 | Yet to be started | 2 hrs
12 | Notifications (Email) | Day 13 | Yet to be started | 1 hr
13 | User dashboard | Day 13–14 | Yet to be started | 2 hrs
14 | Admin – Menu management | Day 14–15 | Yet to be started | 2 hrs
15 | Admin – Order management | Day 15–16 | Yet to be started | 2 hrs
16 | Admin – ZIP control | Day 16 | Yet to be started | 1 hr
17 | Compliance pages | Day 16 | Yet to be started | 0.5 hr
18 | Security & validation | Day 17 | Yet to be started | 1.5 hrs
19 | Testing + bug fixing | Day 17–18 | Yet to be started | 2 hrs
20 | Deployment | Day 18 | Yet to be started | 1 hr

## Shero US Phase 3 - Timeline
Shero App Plan Phase 1- Timeline
S.no | Page/Section/Function | Timeline | Status | Estimated Hours | Hours Taken
1 | Project setup (Next.js + Prisma + Postgres) | Day 1 | Yet to be started | 2 hrs
2 | DB schema design | Day 2–3 | Yet to be started | 3 hrs
3 | UI/UX – Lovable screens integration | Day 3–6 | Yet to be started | 8 hrs
4 | Auth system (Login/Signup + session) | Day 5–6 | Yet to be started | 3 hrs
5 | Homepage + ZIP validation | Day 6–7 | Yet to be started | 2 hrs
6 | Delivery radius logic | Day 7 | Yet to be started | 1.5 hrs
7 | Menu API + UI binding | Day 8–9 | Yet to be started | 3 hrs
8 | Cart system | Day 9–10 | Yet to be started | 2 hrs
9 | Checkout flow | Day 10–11 | Yet to be started | 3 hrs
10 | Stripe payment integration | Day 11–12 | Yet to be started | 3 hrs
11 | Order placement + DB | Day 12 | Yet to be started | 2 hrs
12 | Notifications (Email) | Day 13 | Yet to be started | 1 hr
13 | User dashboard | Day 13–14 | Yet to be started | 2 hrs
14 | Admin – Menu management | Day 14–15 | Yet to be started | 2 hrs
15 | Admin – Order management | Day 15–16 | Yet to be started | 2 hrs
16 | Admin – ZIP control | Day 16 | Yet to be started | 1 hr
17 | Compliance pages | Day 16 | Yet to be started | 0.5 hr
18 | Security & validation | Day 17 | Yet to be started | 1.5 hrs
19 | Testing + bug fixing | Day 17–18 | Yet to be started | 2 hrs
20 | Deployment | Day 18 | Yet to be started | 1 hr

## Shero US Phase 4 - Timeline
Shero App Plan Phase 1- Timeline
S.no | Page/Section/Function | Timeline | Status | Estimated Hours | Hours Taken
1 | Project setup (Next.js + Prisma + Postgres) | Day 1 | Yet to be started | 2 hrs
2 | DB schema design | Day 2–3 | Yet to be started | 3 hrs
3 | UI/UX – Lovable screens integration | Day 3–6 | Yet to be started | 8 hrs
4 | Auth system (Login/Signup + session) | Day 5–6 | Yet to be started | 3 hrs
5 | Homepage + ZIP validation | Day 6–7 | Yet to be started | 2 hrs
6 | Delivery radius logic | Day 7 | Yet to be started | 1.5 hrs
7 | Menu API + UI binding | Day 8–9 | Yet to be started | 3 hrs
8 | Cart system | Day 9–10 | Yet to be started | 2 hrs
9 | Checkout flow | Day 10–11 | Yet to be started | 3 hrs
10 | Stripe payment integration | Day 11–12 | Yet to be started | 3 hrs
11 | Order placement + DB | Day 12 | Yet to be started | 2 hrs
12 | Notifications (Email) | Day 13 | Yet to be started | 1 hr
13 | User dashboard | Day 13–14 | Yet to be started | 2 hrs
14 | Admin – Menu management | Day 14–15 | Yet to be started | 2 hrs
15 | Admin – Order management | Day 15–16 | Yet to be started | 2 hrs
16 | Admin – ZIP control | Day 16 | Yet to be started | 1 hr
17 | Compliance pages | Day 16 | Yet to be started | 0.5 hr
18 | Security & validation | Day 17 | Yet to be started | 1.5 hrs
19 | Testing + bug fixing | Day 17–18 | Yet to be started | 2 hrs
20 | Deployment | Day 18 | Yet to be started | 1 hr

## Shero US Phase 1 - Queries
S No | Page/Section/Function | Part | Description

## Shero US Phase 2 - Queries
S No | Page/Section/Function | Part | Description

## Shero US Phase 3 - Queries
S No | Page/Section/Function | Part | Description

## Shero US Phase 4 - Queries
S No | Page/Section/Function | Part | Description

## Phase 1 - Requirement
| Required | Description | Staus
1 | Full functional & logic document | We need it the understanding of what we require and keep us in check that we are in right track | Yet to get
2 | VPS server setup & access | This will be used for the developement of our web app | Yet to get
3 | Payment gateway details | To integrate the payment to orders.. We should register it with an thirdparty payment gateway provider if we dont have one | Yet to get
4 | Sms gateway | This will be used to SMS communications like OTP, order placement etc.. Same like payment gateway we need to register sms in third party providers | Yet to get
5 | SMTP buisness mail ID | This will act as our from mail ID for the communication to users | Yet to get
6 | All related API's & data's | API's that are necessary for the party orders flow like products, POS connection API etc | Yet to get

## Phase 1 - Timeline
Shero App Plan Phase 1- Timeline
S.no | Page/Section/Function | Timeline | Status | Estimated Hours | Hours Taken
1 | Application setup | 2days | Yet to be started | 2hrs
2 | Backend application & architecture plan | 4days | Yet to be started | 8hrs
3 | Party order flow page 1 - Personal details - Login/Signup | 2days | Yet to be started | 3hrs
4 | Party order flow page 2 - Meal selction flow - Service type | 3days | Yet to be started | 5hrs
5 | Party order flow page 3 - Meal selction flow - Food type |  | Yet to be started
6 | Party order flow page 4 - Meal selction flow - Session |  | Yet to be started
7 | Party order flow page 5 - Meal selction flow - Food selection |  | Yet to be started
8 | Party order flow page 7 - Meal selction flow - Summary |  | Yet to be started
9 | Party order flow page 8 - Meal selction flow - Summary - Discount, Offers, Coupons etc? | 3days | Yet to be started | 1hr
10 | Party order flow page 8 - Meal selction flow - Pay & Place order |  | Yet to be started | 1hr
11 | Party order flow page 7 - Meal selction flow - Order placed, Notifications(SMS & Email), Invoice generations |  | Yet to be started | 2hrs
Admin Dashboard
1 | Party orders menu's handling from dashboard or API
2 | Party orders handling
3 | Reports
User Dashboard
1 | Party orders details
Note : Timeline may change based on detailed /full requirement

## Phase 1 - Queries
S No | Page/Section/Function | Part | Description
1 | Party order flow page 6 - Meal selction flow - Summary | Pdf, Whatsapp, Share, Save, Chat with agent | How does these work & its functional requirement
2 | Party orders menu's handling |  | Are we going to manage party orders menu from API or Dashboard
3 | Server setup done by |  | Will the full server and application setup done by team
4 | Admin dashboard & user dashboard |  | Ui/ux & functional requirements